## Project Timeline
YOUR PROJECT
TIMELINE
PROJECT DETAILS
DATE | MILESTONE | POSITION | BASELINE
2015-08-31 | Project Start | -5 | 1
2015-09-07 | Team Meeting; 1st homework started | 5 | 1
2015-09-14 | Homework #1 Due! | 10 | 1
2015-09-21 | Homework #2 Due | 15 | 1
2015-09-28 | Homework #3 Due | 20 | 1
2015-10-05 | UML diags final; proj plan final | 5 | 1
2015-10-12 | Database design draft | 10 | 1
2015-10-19 | Mid-semester peer reviews due | 15 | 1
2015-10-26 | Draft IT requirements, including network design | 5 | 1
2015-11-02 | Homework #4 Due | 10 | 1
2015-11-09 | First Demo of Prototype | -5 | 1
2015-11-16 | User Validation & Test plan finalized | 10 | 1
2015-11-23 | Client Visit | -5 | 1
2015-11-30 | Draft Documentation | 5 | 1
2015-12-07 | Paper Due - Final Documentation | 10 | 1
2015-12-14 | FINAL PRESENTATION! | -5 | 1
Project Timeline Tips:
The role of the Position values in the Project Details table is to prevent the Milestone labels from overlapping each other on the timeline. Use positive numbers to position labels above the timeline and negative numbers to position them below.
To add additional Milestones, either insert new rows within the table or start typing below the last table entry and the table will automatically expand to accommodate your newly added data.

## Project Plan Details
Date | Milestone | Tasks | Responsible | Notes
2016-08-31 | Project Start | Form team: make introductions; inventory skill strengths and weaknesses; forumulate and document initial roles and responsibilities (to be modified as needed later). | All | Tasks Completed
2016-08-31 | Project Start | Schedule 1st team meeting - and attempt to choose recurring team meeting times that work for everyone (can be established later); establish a communications plan (ie. share emails, cell#'s, and establish how you will stay in touch) | All | Tasks Completed. Weekly meetings are to be held prior to capping as well as on weekends as we see fit. Main methods of communication and work tracking are Slack, Github, and LucidChart.
2016-08-31 | Project Start | Further develop this project plan- Think through our time management and what we will accomplish as the weeks progress. | All | Basic plan layed out. Will likely change as we progress.
2016-09-07 | Team Meeting; 1st homework started | Have met at least once by the end of the day on 9/7; have started Homework #1 minimally | All | Homework 1 has been started
2016-09-10 | Set up IT and Development Environments | Set up the github repository, pick and configure development tools | Ethan Turkeltaub & Max Bender | Ethan has been doing a lot to set up the development environmet and github repository.
2016-09-10 | Finalize Actors/Actions for Use Case Diagram | Have met to agree upon final actors and the actions that they can take by interacting with Amable | All | Met to confirm actors as Potential User, Active User, Moderator, and Admin. This also led to a discussion about tables and attributes for our E-R diagram.
2016-09-14 | Homework #1 Due! | Have HW1 done; Have this project plan completely filled in for review and comments back so we will know if we have a good plan to get to end-game. Having already interveiwd the client format notes from the interview to guide the project. | All | Complete.
2016-09-14 | E-R Diagram Discussion | Have met to discuss key tables and attributes for the database design. Also have agreed upon relationships and begun work on an E-R Diagram | Max Bender, Ethan Turkeltaub, Chris Cordaro, Jack Barry | We have met to discuss the key tables and their attributes as well as the relationships between tables. Jack has started on a basic design of the E-R diagram and hopes to have a first complete draft delivered to the developers by the end of the week as seen in the next task.
2016-09-16 | Complete E-R Diagram and documentation | Have a completed E-R Diagram to be handed to back end developers so that our data infrastructure can begin being built. | Jack Barry
2016-09-20 | Complete list of IT requirements | Have a comprehensive list of IT requirements that will be needed to complete the project. | Dan Jast
2016-09-21 | Homework #2 Due | E-R diagrams complete with supporting documentation if explanation is required for anything you document in your diagrams.As well as a final list of IT requirments. Be ready to speak to both in weekly status report. | Jack Barry & Dan Jast
2016-09-24 | Design & Database Discussion | Have met to discuss general layout of the UI and what functionality needs to be built into the interface to create a positive user experience. This or a separate meeting will also cover beginning steps for database development | All
2016-09-26 | Completed drafts of wireframes | Have 5 wireframe drafts completed for team review. | Chris Cordaro & Ethan Turkeltaub
2016-09-26 | Wireframe Review | Have met to review the wireframe desgins | All
2016-09-28 | Homework #3 Due | Complete mock-ups (ie. wireframes) of your user interface that have been updated based on team review. | Chris Cordaro & Ethan Turkeltaub
2016-09-30 | Basic databace instratructure complete | Have the infrastructure of the database built with the correct tables and attributes. | Max Bender, Ethan Turkeltaub
2016-10-02 | Connect database to front end UI | Have met to review and begin the process of coding interaction between the UI and the backend database. | Max Bender, Ethan Turkeltaub, Chris Cordaro
2016-10-05 | UML diags final; proj plan final | Final Project Plan - updated with all input from instructor Final UML Diagrams | Jack Barry
2016-10-08 | Begin drafting final paper | Have met to discuss the scope and format of the final paper. | All
2016-10-10 | Development check in | Have met to review the database design and become comfortable enough with it to present about it during the weekly status report on 10/12/2016 | All
2016-10-12 | Database design draft | Draft database design. Database design will be the focus of this weeks status report. | Max Bender, Ethan Turkeltaud, Chris Cordaro
2016-10-16 | IT Scalability Check in | Review IT requirments and make sure that the existing environmant can scale to the user requirements. | Dan Jast
2016-10-18 | General Meeting | Have met to dicuss progress and obstacles encountered during development process | All
2016-10-19 | Mid-semester peer reviews due | Complete initial (ie. first pass feedback) peer reviews | All
2016-10-24 | General Meeting & Code review | Have met to discuss progress and obstacles during development process. The team will also review existing code for readability, efficiency, and format. | All
2016-10-26 | Draft IT requirements, including network design | Network design diagrams complete using Lucid chart. | Dan Jast
2016-10-31 | Network Design Documentation | Network design now has complete documentation | Jack Barry & Dan Jast
2016-10-31 | Finalize Database Design | Have met to discuss updates made to the databse design based on instructor feedback. Document these updates for housekeeping | All
2015-11-02 | Homework #4 Due | Database prototype complete | Max Bender, Ethan Turkeltaub, Chris Cordaro
2015-11-09 | First Demo of Prototype | Complete project prototype first-pass demo ready | All
2015-11-16 | User Validation & Test plan finalized | Test plan for all aspects of the prototype complete User validation tests to be performed by client documented | Ethan Turkeltaub & Max Bender
2015-11-23 | Client Visit | Updates to user validation complete (as required) One key question to ask the client dcoumented | All
2015-11-30 | Draft Documentation | All documentation required for the project in Draft form | Jack Barry & Dan Jast
2015-12-07 | Paper Due - Final Documentation | All documentation required for the project in FINAL form | Jack Barry & Dan Jast
2015-12-07 | Final Peer Evaluations | Complete final peer evaluation forms and submit | All
2015-12-14 | FINAL PRESENTATION! | Git er dun! | All

## Week Class Sched - Fall2015
Week | Class Topics and Activities | Assignments Due | Class Format
8/31 | Introduction; Project case study; Project plan; |  | Group (HC2023)
Sections and Teams; Project overview
9/7 | NO CLASS: Labor Day
9/14 | Client Interview | Homework 1 due | Group (HC2023)
9/21 | SME visit | Team status report
Brown bag session
Homework 2 due
9/28 | Project Management and UML | Team status report | Group (HC2023)
Brown bag session
Homework 3 due
10/5 | Guest presentation: Alan Labouseur - database | Team status report | Group (HC2023)
Brown bag session
10/12 |  | Team status report | HC2023 available
|  | Brown bag session | if needed
10/19 | Networking | Team status report | Group (HC2023)
| Draft peer-reviews | Brown bag session
10/26 |  | Team status report
Brown bag session
11/2 |  | Team status report: Database | HC2023 available
|  | Homework 4 due | if needed
11/9 | Prototype 1st Demonstration | Rough draft demo presentations
11/16 | User Validation & Test Planning |  | Group (HC2023)
11/23 | Client visit | Team status report
Brown bag session
11/30 | SME visit | Team status report
| Draft documentation / paper | Brown bag session
12/7 | Final documentation / paper | Brown bag session
| Final peer-reviews | Project paper due
Peer evaluations due
12/14 | Project presentations | Project prototype due
Project presentations

## Weekly Status Reports
Status Report - Team name, members
Date 9/14/2016
RGY | Item | Description | Mitigation / Help needed
Green | Form Team | Gather an eilte team of technology professionals
Green | Exchange contact info. | Establish method of communication - Slack & Github
Green | Initial meeting | Meet to discuss responsibilities and timelines
Green | Project Planning | After initial meeting we can now lay out project goals and tasks in a formal way
Green | UML Use Case Diagram | Create use case diagram and supporting documentation to represent agreed upon actors and the actions they can perform by interacting with Amable.
Green | Database Discussion | Discuss key tables and attributes that we want to be included in our database design. Also discuss the nature of the relationships between out tables.
Green | IT requiremnts Documentation | Gather and document requirements from an IT perspective so that we know how to plan and scale development.
Yellow | E-R Diagram | Creae an E-R diagram with supporting documentation that represents out database design | Jack is working on the E-R diagram and is only limited by time contraints. Hope to have the diagram finished by the end of the week so that Max, Ethan, and Chris can begin working on development.
Red